|  |
| --- |
| Combined Sewage Storage Tunnel (CSST) Site 5 Projected Construction Sequencing Summary |
| As of July 7, 2017 |
| This table should be considered to be a living document and presents a best estimate based on the Contractor's submitted construction schedule and the project team's general experience with similar activities. Contractually, the Contractor is NOT required to adhere to this detailed schedule. The Contractor will be submitting detailed schedules and management plans prior to undertaking each main component of this work. |

| **Task (1)** | **Work Location** | **Start Date** | **End Date** | **Duration** | **Details of Work** | **Truck and Noise (2)** |
| --- | --- | --- | --- | --- | --- | --- |
| **November 2016** |
| IOS Locating & Phase 2 Archaeological Investigation | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid November 2016 | Early December 2016 | 2-3 weeks (COMPLETE) | Drill rig will be setup in Stanley Park to core down and find exact location of existing 15m-deep trunk sewer (IOS). Drill rigs used to core down are not excessively noisy. Daytime drilling expected. Little to no material trucking - just drilling crew. Access along pathway. During roughly same period, a Stage 2 archaeological investigation will take place. | Modest noise. Negligible trucking. |
| **December 2016** |
| IOS Locating & Phase 2 Archaeological Investigation | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid November 2016 | Early December 2016 | 2-3 weeks (COMPLETE) | Drill rig will be setup in Stanley Park to core down and find exact location of existing 15m-deep trunk sewer (IOS). Drill rigs used to core down are not excessively noisy. Daytime drilling expected. Little to no material trucking - just drilling crew. Access along pathway. During roughly same period, a Stage 2 archaeological investigation will take place. | Modest noise. Negligible trucking. |
| **March 2017** |
| Tree Clearing | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early March 2017 | Late March 2017 | 2-3 weeks (COMPLETE) | Activities would be limited to clearing of larger trees outside of the bird nesting season. Stumps and smaller brushes would be left on site for later removal. Tree grabbers, chainsaws, tub grinders and grinders for branches will be used at the site. There will be some noise due to grinding and from the engine of the tub grinder. Daytime work only. Trucking will include hauling felled trees and mulch off site. | Some noise from tree cutting. Modest trucking. |
| Traffic Control, Hoarding/Fencing, Site Setup, Tree Protection | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early March 2017 | Mid May 2017 | 7-8 weeks (COMPLETE) | Site setup activities, including installation of the hoarding/fencing and tree protection measures. Modest trucking (fence delivery, etc) and noise. | Modest noise. Negligible trucking. |
| **April 2017** |
| Traffic Control, Hoarding/Fencing, Site Setup, Tree Protection | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early March 2017 | Mid May 2017 | 7-8 weeks (COMPLETE) | Site setup activities, including installation of the hoarding/fencing and tree protection measures. Modest trucking (fence delivery, etc) and noise. | Modest noise. Negligible trucking. |
| Build and Grade Temporary Access Roads & Pathways | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2017 | Late April 2017 | 3-4 weeks (COMPLETE) | Converting the pathway to truck access route (making it more robust), and constructing pathway detours for park users. Will include hauling granular material (3-4 trucks per hour for about a week) and spreading the granular material (bulldozer/grader). Additionally, there would be 3-4 empty trucks per hour leaving the site. Some multi-use temporary pathways also require paving (small pathway paving equipment - one day). | Modest noise. Heavier trucking. |
| Traffic Control, Hoarding/Fencing, Site Setup, Tree Protection | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early April 2017 | Mid to late June 2017 | 12 weeks (COMPLETE) | Site setup activities, including installation of the fencing and relocation of utilities and sewers as required. Some noise during hoarding installation and modest trucking (delivery of fences/piping, hauling away of some material excavated for these relocations, etc). | Modest noise. Negligible trucking. |
| **May 2017** |
| Traffic Control, Hoarding/Fencing, Site Setup, Tree Protection | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early March 2017 | Mid May 2017 | 7-8 weeks (COMPLETE) | Site setup activities, including installation of the hoarding/fencing and tree protection measures. Modest trucking (fence delivery, etc) and noise. | Modest noise. Modest trucking. |
| Construction of Secant Wall | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early May 2017 | Mid June 2017 | 4-6 weeks (COMPLETE) | Secant wall is a circular watertight enclosure around a deep excavation area (e.g. for a chamber). It is installed before removing the earth in order to mitigate affecting the groundwater table around the excavation. Activities consists of drilling vertically into soil, installing secant piles in a large circle and grouting the circumference to make the chamber area watertight. Handling of the seccant piles could generate some noise. Noise Bylaw limits apply to any nighttime work. Marginal trucking for materials and some soils. A small amount of potentially contaminated soil may require disposal off-site during this phase. | Some loud noise associated with driving sheet piles. Modest trucking. |
| Utility Relocation | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Mid May 2017 | Early July 2017 | 4-6 weeks | Relocation of communication lines by the utility companies from above-ground to underground. | Some noise due to rock excavation. Modest trucking. |
| Traffic Control, Hoarding/Fencing, Site Setup, Utility Relocation and Temporary Sewer Bypass | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early April 2017 | Mid to late June 2017 | 12 weeks (COMPLETE) | Site setup activities, including installation of the fencing and relocation of utilities and sewers as required. Some noise during hoarding installation and modest trucking (delivery of fences/piping, hauling away of some material excavated for these relocations, etc). | Modest noise. Modest trucking. |
| **June 2017** |
| Construction of Secant Wall | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early May 2017 | Mid June 2017 | 4-6 weeks (COMPLETE) | Secant wall is a circular watertight enclosure around a deep excavation area (e.g. for a chamber). It is installed before removing the earth in order to mitigate affecting the groundwater table around the excavation. Activities consists of drilling vertically into soil, installing the secant piles in a large circle and grouting the circumference to make the chamber area watertight. Handling of the secant piles could generate some noise. Noise Bylaw limits apply to any nighttime work. Marginal trucking for materials and some soils. A small amount of potentially contaminated soil may require disposal off-site during this phase.  | Some loud noise associated with driving sheet piles. Modest trucking. |
| Construction of Odour Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required.  | Modest noise. Modest trucking. |
| Utility Relocation | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Mid May 2017 | Early July 2017 | 4-6 weeks | Relocation of communication lines by the utility companies from above-ground to underground. | Some noise due to rock excavation. Modest trucking. |
| Traffic Control, Hoarding/Fencing, Site Setup, Utility Relocation and Temporary Sewer Bypass | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early April 2017 | Mid to late June 2017 | 12 weeks (COMPLETE) | Site setup activities, including installation of the fencing and relocation of utilities and sewers as required. Some noise during hoarding installation and modest trucking (delivery of fences/piping, hauling away of some material excavated for these relocations, etc). | Modest noise. Modest trucking. |
| **July 2017** |
| Noise Barrier Construction | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Late July 2017 | Mid to Late August 2017 | 3-4 weeks | Erection of noise barrier system around the perimeter of Site 5c. Work activities will include installation of pilin for foundations, construction of metal framing, and hanging of sound barrier material. | Some loud noise associated with foundation piling. Modest trucking.  |
| Utility Relocation | Site 5c (Rideau River Collector -  |  |  |  |  |  |
| Shoring | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early to Mid August 2017 | Early September 2017 | 2-4 weeks | Includes driving shoring piles into the soil down to the rock elevation and line grouting to permit excavation of soils inside the shored area while supporting the surrounding areas. Installing the shoring will generate some noise - limited to daytime. Modest trucking - limited to hauling shoring material and perhaps some small volume of soils may be hauled away. | Some noise (relatively modest) due to excavating equipment and soil moving. |
| Noise Barrier Construction | Site 5b (Stanley Park - Closer to Queen Victoria Access) | Late July 2017 |  Mid August 2017 | 2-3 weeks | Erection of noise barrier system on both sides of the 5b construction access gate. Work activities will include installation of fence posts, and construction of wood sound barrier materials. | Modest noise. Modest trucking.  |
| Earth Excavation | Site 5b (Stanley Park – Closer to Queen Victoria Access) | Mid July 2017 | Late July 2017 |  1 week | Once shoring is installed, the earth material will be excavated and trucked away (maybe 3 trucks per hour for 3-4 days – small volume). The same frequency of empty trucks would also return to the site. Note that some potentially contaminated material could be encountered during the earth excavation for trucking and disposal off-site. | Modest Noise. Heavier trucking (very short duration) when moving soil. |
| Rock Excavation | Site 5b (Stanley Park - Closer to Queen Victoria Access) | Late July 2017 | Mid to Late August 2017 | 3-4 weeks | Rock excavation will involve drilling, blasting, shotcrete and bolt installation, as well as trucking away excavated rock. Trucking frequency will be low as rock removal is a slow operation compared to earth removal. No rock can be handled (stored and/or removed off-site) afterhours due to noise limit bylaws. | Some loud noise from breaking rock. Modest trucking. |
| Earth Excavation | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early July 2017 | Mid August 2017 | 4-6 weeks | Once secant walls are built, the earth inside will be removed in order to build the chambers and will be trucked off-site. Some potentially contaminated material could be encountered during the earth excavation for trucking and disposal off-site. Applies to 2 chamber locations at Site 5a (main area). Expect to generate 3-4 trucks per hour hauling excavated earth off-site. Trucks must pass through wash bay prior to exiting the site. There will also be another 3-4 empty trucks returning to the site each hour during this period. | Modest noise. Heavier trucking. |
| Installation of Collar Beam | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Late July 2017 | Mid August 2017 | 2-3 weeks | Shoring for deep excavations. No trucking other than bringing some material in. | Modest Noise. Negligible trucking. |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| **August 2017** |
| Earth Excavation | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early July 2017 | Mid August 2017 | 4-6 weeks | Once secant walls are built, the earth inside will be removed in order to build the chambers and will be trucked off-site. Some potentially contaminated material could be encountered during the earth excavation for trucking and disposal off-site. Applies to 2 chamber locations at Site 5a (main area). Expect to generate 3-4 trucks per hour hauling excavated earth off-site. Trucks must pass through wash bay prior to exiting the site. There will also be another 3-4 empty trucks returning to the site each hour during this period. | Modest noise. Heavier trucking. |
| Installation of Collar Beam | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Late July 2017 | Mid August 2017 | 2-3 weeks | Shoring for deep excavations. No trucking other than bringing some material in. | Modest noise. Negligible trucking. |
| Rock Excavation | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid August 2017 | Late October 2017 | 8-10 weeks | Rock excavation will involve drilling, blasting, shotcrete and bolt installation, as well as trucking away excavated rock. Trucking frequency will be low as rock removal is a slow operation compared to earth removal. No rock can be handled (stored and/or removed off-site) afterhours due to Noise Bylaw limits. | Some loud noise from breaking rock. Modest trucking. |
| Noise Barrier Construction | Site 5c (Rideau River Collection – Overflow Diversion Chamber – At Intersection of River Lane & Queen Victoria (4) | Late July 2017 | Mid to Late August 2017 | 3-4 weeks | Erection of noise barrier system around the perimeter of Site 5c. Work activities will include installation of pilin for foundations, construction of metal framing, and hanging of sound barrier material. | Some loud noise associated with foundation piling. Modest Trucking. |
| Shoring | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Mid August 2017 | Early September 2017 | 2-4 weeks | Includes driving shoring piles into the soil down to the rock elevation and line grouting to permit excavation of soils inside the shored area while supporting the surrounding areas. Installing the shoring will generate some noise - limited to daytime. Modest trucking - limited to hauling shoring material and perhaps some small volume of soils may be hauled away. | Some noise (relatively modest) due to excavating equipment and soil moving.  |
| Earth Excavation | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early August 2017 | Early August 2017 | 1 week | Once shoring is installed, the earth material will be excavated and trucked away (maybe 2-3 trucks per hour - small volume). The same frequency of empty trucks would also return to the site. | Modest noise. Heavier trucking. |
| Rock Excavation | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early August 2017 | Early October 2017 | 8 weeks | Rock excavation will involve drilling, blasting, hoe- ramming, shotcrete and bolt installation, as well as trucking away excavated rock. Trucking frequency will be low as rock removal is a slow operation compared to earth removal. | Loud noise resulting from hoe-ramming and rock handling. Modest trucking. |
| Noise Barrier Construction | Site 5b (Stanley Park – Closer to Queen Victoria Access) | Mid to Late July 2017 | Mid August 2017 | 2-3 Weeks | Erection of noise barrier system on both sides of the 5b construction access gate. Work activities will include installation of fence posts, and construction of wood sound barrier materials. | Modest noise. Modest trucking. |
| Rock Excavation | Site 5b (Stanley Park - Closer to Queen Victoria Access) | Late July 2017 | Mid to Late August 2017 | 3-4 weeks | Rock excavation will involve drilling, blasting, shotcrete and bolt installation, as well as trucking away excavated rock. Trucking frequency will be low as rock removal is a slow operation compared to earth removal. No rock can be handled (stored and/or removed off-site) afterhours due to noise limit bylaws. | Some loud noise from breaking rock. Modest trucking. |
| MicroTunnel Launch Shaft Setup, Shoring Installation | Site 5b (Stanley Park - Closer to Queen Victoria Access) | Mid to Late August 2017 | Mid September 2017 | 2-3 weeks | This is for the diversion sewer that will divert overflows away from Ottawa River and into the CSST. There will be a sewer installed by tunneling between Stanley Park and the intersection of River Lane / Queen Victoria. Activities for this phase include installing shoring into the soil to prepare for excavation of the hole. | Some loud noise associated with driving sheet piles. Modest trucking. |
| Rock Excavation | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid August 2017 | Late October 2017 | 8 -10 weeks | Rock excavation will involve drilling, blasting, shotcrete and bolt installation. Trucking frequency will be low as rock removal is a slow operation compared to earth removal. No rock can be handled (stored and/or removed off-site) afterhours due to Noise Bylaw limits. | Some loud noise from breaking rock. Modest trucking. |
| **September 2017** |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| Micro-Tunneling of Diversion Sewer (5b to River Lane) | Site 5b (Stanley Park - Closer to Queen Victoria Access) | Early September 2017 | Late November 2017 | 8-10 weeks | Includes installation of tunneling equipment, pilot hole tunneling, back reaming along that pilot hole, and finishing the grouting. The back reaming operation (which consists of enlarging the smaller pilot hole to the size required for the sewer) is expected to produce the most trucking as it generates spoils (crushed rock) to be hauled away, and will last approximately 5-6 weeks. For this section of the diversion tunnel, it is proposed by the contractor that these reaming spoils be extracted from the shaft located that the intersection of River Lane / Queen Victoria - to be confirmed. Could fill four trucks per day at its peak. | Some modest noise associated with motor for auger. Modest trucking. |
| Shoring | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Mid August 2017 | Early September 2017 | 2-4 weeks | Includes driving shoring piles into the soil down to the rock elevation and line grouting to permit excavation of soils inside the shored area while supporting the surrounding areas. Installing the shoring will generate some noise - limited to daytime. Modest trucking - limited to hauling shoring material and perhaps some small volume of soils may be hauled away. | Some noise (relatively modest) due to excavating equipment and soil moving. |
| Rock Excavation | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early August 2017 | Mid October 2017 | 8 weeks | Rock excavation will involve drilling, blasting, hoe- ramming, shotcrete and bolt installation, as well as trucking away excavated rock. Trucking frequency will be low as rock removal is a slow operation compared to earth removal. | Loud noise resulting from hoe-ramming and rock handling. Modest trucking. |
| Micro-Tunneling of Diversion Sewer (5b to River Lane) | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early September 2017 | Late November 2017 | 8-10 weeks | Includes installation of tunneling equipment, pilot hole tunneling, back reaming along that pilot hole, and finishing the grouting. The back reaming operation (which consists of enlarging the smaller pilot hole to the size required for the sewer) is expected to produce the most trucking as it generates spoils (crushed rock) to be hauled away, and will last approximately 5-6 weeks. For this section of the diversion tunnel, it is proposed by the contractor that these reaming spoils be extracted from the shaft located that the intersection of River Lane / Queen Victoria - to be confirmed. Could fill four trucks per day at its peak. | Some modest noise associated with motor for auger. Modest trucking. |
| Rock Excavation | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid August 2017 | Late October 2017 | 8 -10 weeks | Rock excavation will involve drilling, blasting, shotcrete and bolt installation. Trucking frequency will be low as rock removal is a slow operation compared to earth removal. No rock can be handled (stored and/or removed off-site) afterhours due to Noise Bylaw limits. | Some loud noise from breaking rock. Modest trucking. |
| **October 2017** |
| Micro-Tunneling of Diversion Sewer (5b to River Lane) | Site 5b (Stanley Park - Closer to Queen Victoria Access) | Early September 2017 | Late November 2017 | 8-10 weeks | Includes installation of tunneling equipment, pilot hole tunneling, back reaming along that pilot hole, and finishing the grouting. The back reaming operation (which consists of enlarging the smaller pilot hole to the size required for the sewer) is expected to produce the most trucking as it generates spoils (crushed rock) to be hauled away, and will last approximately 5-6 weeks. For this section of the diversion tunnel, it is proposed by the contractor that these reaming spoils be extracted from the shaft located that the intersection of River Lane / Queen Victoria - to be confirmed. Could fill four trucks per day at its peak. | Some modest noise associated with motor for auger. Modest trucking. |
| Setup Tunnel Launch Shaft | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Late October 2017 | Early January 2018 | 8-10 weeks | Includes pouring mud slab, hand-mining tail tunnel. Will include trucking, but low frequency due to slow progress of hand-mining 25-30m long tail tunnel to prepare for the Tunnel Boring Machine (TBM) insertion. Modest noise would include handling of excavated rock (loading trucks). No rock can be handled (stored and/or removed off-site) afterhours due to Noise Bylaw limits. | Modest noise. Modest trucking. |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| Rock Excavation | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early August 2017 | Mid October 2017 | 8 weeks | Rock excavation will involve drilling, blasting, hoe- ramming, shotcrete and bolt installation, as well as trucking away excavated rock. Trucking frequency will be low as rock removal is a slow operation compared to earth removal. | Loud noise resulting from hoe-ramming and rock handling. Modest trucking. |
| Micro-Tunneling of Diversion Sewer (5b to River Lane) | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early September 2017 | Late November 2017 | 8-10 weeks | Includes installation of tunneling equipment, pilot hole tunneling, back reaming along that pilot hole, and finishing the grouting. The back reaming operation (which consists of enlarging the smaller pilot hole to the size required for the sewer) is expected to produce the most trucking as it generates spoils (crushed rock) to be hauled away, and will last approximately 5-6 weeks. For this section of the diversion tunnel, it is proposed by the contractor that these reaming spoils be extracted from the shaft located that the intersection of River Lane / Queen Victoria - to be confirmed. Could fill four trucks per day at its peak. | Some modest noise associated with motor for auger. Modest trucking. |
| Setup Tunnel Launch Shaft | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Late October 2017 | Early January 2018 | 8-10 weeks | Includes pouring mud slab, hand-mining tail tunnel. Will include trucking, but low frequency due to slow progress of hand-mining 25-30m long tail tunnel to prepare for the Tunnel Boring Machine (TBM) insertion. Modest noise would include handling of excavated rock (loading trucks). No rock can be handled (stored and/or removed off-site) afterhours due to Noise Bylaw limits. | Modest noise. Modest trucking. |
| **November 2017** |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| Micro-Tunneling of Diversion Sewer (5b to River Lane) | Site 5b (Stanley Park - Closer to Queen Victoria Access) | Early September 2017 | Late November 2017 | 8-10 weeks | Includes installation of tunneling equipment, pilot hole tunneling, back reaming along that pilot hole, and finishing the grouting. The back reaming operation (which consists of enlarging the smaller pilot hole to the size required for the sewer) is expected to produce the most trucking as it generates spoils (crushed rock) to be hauled away, and will last approximately 5-6 weeks. For this section of the diversion tunnel, it is proposed by the contractor that these reaming spoils be extracted from the shaft located that the intersection of River Lane / Queen Victoria - to be confirmed. Could fill four trucks per day at its peak. | Some modest noise associated with motor for auger. Modest trucking. |
| Micro-Tunneling of Diversion Sewer (5b to River Lane) | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early September 2017 | Late November 2017 | 8-10 weeks | Includes installation of tunneling equipment, pilot hole tunneling, back reaming along that pilot hole, and finishing the grouting. The back reaming operation (which consists of enlarging the smaller pilot hole to the size required for the sewer) is expected to produce the most trucking as it generates spoils (crushed rock) to be hauled away, and will last approximately 5-6 weeks. For this section of the diversion tunnel, it is proposed by the contractor that these reaming spoils be extracted from the shaft located that the intersection of River Lane / Queen Victoria - to be confirmed. Could fill four trucks per day at its peak. | Some modest noise associated with motor for auger. Modest trucking. |
| Setup Tunnel Launch Shaft | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Late October 2017 | Early January 2018 | 8-10 weeks | Includes pouring mud slab, hand-mining tail tunnel. Will include trucking, but low frequency due to slow progress of hand-mining 25-30m long tail tunnel to prepare for the Tunnel Boring Machine (TBM) insertion. Modest noise would include handling of excavated rock (loading trucks). No rock can be handled (stored and/or removed off-site) afterhours due to Noise Bylaw limits. | Modest noise. Modest trucking. |
| **December 2017** |
| Inserting and Setting up TBM | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early December 2017 | Early April 2018 | 12-14 weeks | Delivery of TBM to site (in pieces), inserting into the launch shaft, reassembly, prepare for launch. Other than trucking in the TBM pieces and associated support equipment/materials, limited trucking and limited noise. | Modest noise. Modest trucking. |
| Micro-Tunneling of Diversion Sewer (5b to EWT Outlet Chamber - main shaft) | Site 5b (Stanley Park - Closer to Queen Victoria Access) | Mid Dec 2017 | Mid Feb 2017 | 8 weeks | Includes Installation of tunneling equipment, plus 2-3 weeks of pilot hole tunneling, 5-6 weeksof back reaming alog that pilot hole, and finishing the grouting. The reaming operation (which consists of enlarging the smaller pilot hole to the size required for the sewer) is expected to produce the most trucking as it generates spoils (crushed rock) to be hauled away. Could fill one or two trucks per hour at its peak for that 5-6 week period. | Modest noise. Modest trucking. |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| Construction of Chambers (once micro- tunneling complete) | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Mid Dec 2017 | Late March 2018 | 16-18 weeks (4 months) | Construction of chambers includes the following components: structure floor, walls and roof construction, installation of weir, ladders and steps, demolition of section of existing overflow sewer, new connections, backfill and removal of shoring. Materials and concrete being delivered to site as required. This phase includes backfill around the chamber, estimated to generate 3-4 trucks per hour hauling backfill material to the site and the same frequency of empty trucks leaving the site - over a period of approximately 1-2 weeks in late January / early February. Other trucking would include concrete trucks during the pours | Modest noise. Heavier trucking during backfill (1-2 weeks), modest otherwise. |
| Setup Tunnel Launch Shaft | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Late October 2017 | Early January 2018 | 8-10 weeks | Includes pouring mud slab, hand-mining tail tunnel. Will include trucking, but low frequency due to slow progress of hand-mining 25-30m long tail tunnel to prepare for the Tunnel Boring Machine (TBM) insertion. Modest noise would include handling of excavated rock (loading trucks). No rock can be handled (stored and/or removed off-site) afterhours due to Noise Bylaw limits. | Modest noise. Modest trucking. |
| **January 2017** |
| Inserting and Setting up TBM | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early December 2017 | Early April 2018 | 12-14 weeks | Delivery of TBM to site (in pieces), inserting into the launch shaft, reassembly, prepare for launch. Other than trucking in the TBM pieces and associated support equipment/materials, limited trucking and limited noise. | Modest noise. Modest trucking. |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| Micro-Tunneling of Diversion Sewer (5b to EWT Outlet Chamber - main shaft) | Site 5b (Stanley Park - Closer to Queen Victoria Access) | Mid Dec 2017 | Mid Feb 2017 | 8 weeks | Includes installation of tunneling equipment, plus 2- 3 weeks of pilot hole tunneling, 5-6 weeks of back reaming along that pilot hole, and finishing the grouting. The reaming operation (which consists of enlarging the smaller pilot hole to the size required for the sewer) is expected to produce the most trucking as it generates spoils (crushed rock) to be hauled away. Could fill one or two trucks per hour at its peak for that 5-6 week period. | Modest noise. Modest trucking. |
| Construction of Chambers (once micro- tunneling complete) | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Mid Dec 2017 | Late March 2018 | 16-18 weeks (4 months) | Construction of chambers includes the following components: structure floor, walls and roof construction, installation of weir, ladders and steps, demolition of section of existing overflow sewer, new connections, backfill and removal of shoring. Materials and concrete being delivered to site as required. This phase includes backfill around the chamber, estimated to generate 3-4 trucks per hour hauling backfill material to the site and the same frequency of empty trucks leaving the site - over a period of approximately 1-2 weeks in late January / early February. Other trucking would include concrete trucks during the pours | Modest noise. Heavier trucking during backfill (1-2 weeks), modest otherwise. |
| Inserting and Setting up TBM | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early December 2017 | Early April 2018 | 12-14 weeks | Delivery of TBM to site (in pieces), inserting into the launch shaft, reassembly, prepare for launch. Other than trucking in the TBM pieces and associated support equipment/materials, limited trucking and limited noise. | Modest noise. Modest trucking. |
| **February 2018** |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| Micro-Tunneling of Diversion Sewer (5b to EWT Outlet Chamber - main shaft) | Site 5b (Stanley Park - Closer to Queen Victoria Access) | Mid Dec 2017 | Mid Feb 2017 | 8 weeks | Includes installation of tunneling equipment, plus 2- 3 weeks of pilot hole tunneling, 5-6 weeks of back reaming along that pilot hole, and finishing the grouting. The reaming operation (which consists of enlarging the smaller pilot hole to the size required for the sewer) is expected to produce the most trucking as it generates spoils (crushed rock) to be hauled away. Could fill one or two trucks per hour at its peak for that 5-6 week period. | Modest noise. Modest trucking. |
| Installation of 3 m Pre-Cast Shaft | Site 5b (Stanley Park - Closer to Queen Victoria Access)  | Mid February 2018 | Mid March 2018 | 4-6 weeks | Activities include installing the precast chamber sections, benching and grouting, backfilling, removal of shoring, etc. Small chamber - modest trucking. Similar to installing a big sewer manhole with more parging/grouting and a large gate and related equipment on the inside. | Modest noise. Modest trucking. |
| Construction of Chambers (once micro- tunneling complete) | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Mid Dec 2017 | Late March 2018 | 16-18 weeks (4 months) | Construction of chambers includes the following components: structure floor, walls and roof construction, installation of weir, ladders and steps, demolition of section of existing overflow sewer, new connections, backfill and removal of shoring. Materials and concrete being delivered to site as required. This phase includes backfill around the chamber, estimated to generate 3-4 trucks per hour hauling backfill material to the site and the same frequency of empty trucks leaving the site - over a period of approximately 1-2 weeks in late January / early February. Other trucking would include concrete trucks during the pours | Modest noise. Heavier trucking during backfill (1-2 weeks), modest otherwise. |
| Inserting and Setting up TBM | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early December 2017 | Early April 2018 | 12-14 weeks | Delivery of TBM to site (in pieces), inserting into the launch shaft, reassembly, prepare for launch. Other than trucking in the TBM pieces and associated support equipment/materials, limited trucking and limited noise. | Modest noise. Modest trucking. |
| **March 2018** |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| Installation of 3 m Pre-Cast Shaft | Site 5b (Stanley Park - Closer to Queen Victoria Access)  | Mid February 2018 | Mid March 2018 | 4-6 weeks | Activities include installing the precast chamber sections, benching and grouting, backfilling, removal of shoring, etc. Small chamber - modest trucking. Similar to installing a big sewer manhole with more parging/grouting and a large gate and related equipment on the inside. | Modest noise. Modest trucking. |
| Construction of Chambers (once micro- tunneling complete) | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Mid Dec 2017 | Late March 2018 | 16-18 weeks (4 months) | Construction of chambers includes the following components: structure floor, walls and roof construction, installation of weir, ladders and steps, demolition of section of existing overflow sewer, new connections, backfill and removal of shoring. Materials and concrete being delivered to site as required. This phase includes backfill around the chamber, estimated to generate 3-4 trucks per hour hauling backfill material to the site and the same frequency of empty trucks leaving the site - over a period of approximately 1-2 weeks in late January / early February. Other trucking would include concrete trucks during the pours | Modest noise. Heavier trucking during backfill (1-2 weeks), modest otherwise. |
| Grading and Rough Reinstatement | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Late March 2018 | Late April 2018 | 4 weeks | Grading of the surface, base-coat paving, curbs, sidewalks, rough grading of landscaped areas to prepare for sodding later in the spring (since weather will not permit sodding at this time). Opening of the intersection. Heavier trucking will be during delivery of granular material for road construction (3-4 trucks per hour for a week or so). | Modest noise. Heavier trucking for 1- 2 weeks, otherwise modest. |
| Inserting and Setting up TBM | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early December 2017 | Early April 2018 | 12-14 weeks | Delivery of TBM to site (in pieces), inserting into the launch shaft, reassembly, prepare for launch. Other than trucking in the TBM pieces and associated support equipment/materials, limited trucking and limited noise. | Modest noise. Modest trucking. |
| **April 2018** |
| East-West Tunnel (EWT) Tunneling | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2018 | Early February 2019 | 40-45 weeks (10 months) | TBM progressing along EWT. Spoils (crushed stones - gravel) being extracted from launch shaft and being trucked away. Tunneling 20-22 hours per day, but trucking limited to normal working hours of 12- 14 hours (between 7:00AM and 10:00PM). Noise Bylaw limits apply to afterhours activities. Estimate that tunnel spoils will be hauled away at 3 trucks per hour as the tunnel progresses approximately 20 m per day. Another 3 empty trucks will be arriving to the site each hour to be loaded. Tunneling will also require, on average, 3 trucks per day delivering parts for the tunnel lining. | Modest noise. Heavier trucking. |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| Grading around this shaft 5b | Site 5b (Stanley Park - Closer to Queen Victoria Access) | Late April 2018 | Early May 2018 | 2 weeks | Rough grading. Final landscaping is included as part of the landscaping activity described for Site 5a. | Modest noise. Heavier trucking. |
| Grading and Rough Reinstatement | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Late March 2018 | Late April 2018 | 4 weeks | Grading of the surface, base-coat paving, curbs, sidewalks, rough grading of landscaped areas to prepare for sodding later in the spring (since weather will not permit sodding at this time). Opening of the intersection. Heavier trucking will be during delivery of granular material for road construction (3-4 trucks per hour for a week or so). | Modest noise. Heavier trucking for 1- 2 weeks, otherwise modest. |
| East-West Tunnel (EWT) Tunneling | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2018 | Early February 2019 | 40-45 weeks (10 months) | TBM progressing along EWT. Spoils (crushed stones - gravel) being extracted from launch shaft and being trucked away. Tunneling 20-22 hours per day, but trucking limited to normal working hours of 12- 14 hours (between 7:00AM and 10:00PM). Noise Bylaw limits apply to afterhours activities. Estimate that tunnel spoils will be hauled away at 3 trucks per hour as the tunnel progresses approximately 20 m per day. Another 3 empty trucks will be arriving to the site each hour to be loaded. Tunneling will also require, on average, 3 trucks per day delivering parts for the tunnel lining. | Modest noise. Heavier trucking. |
| **May 2018** |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| Grading around this shaft 5b | Site 5b (Stanley Park - Closer to Queen Victoria Access)  | Late April 2018 | Early May 2018 | 2 weeks | Rough grading. Final landscaping is included as part of the landscaping activity described for Site 5a. | Modest noise. Heavier trucking. |
| Post-Construction Final Reinstatement | Site 5c (Rideau River Collector - Overflow Diversion Chamber - At intersection of River Lane & Queen Victoria (4) | Early May 2018 | Mid May 2018 | 1-2 weeks | Once weather is warmer, application of final layer of pavement and placement of sod and plantings. No long-term roadway impact as top-lift pavement is expected to be completed in a single day. | Modest noise. Heavier trucking for 2 days of paving. |
| East-West Tunnel (EWT) Tunneling | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2018 | Early February 2019 | 40-45 weeks (10 months) | TBM progressing along EWT. Spoils (crushed stones - gravel) being extracted from launch shaft and being trucked away. Tunneling 20-22 hours per day, but trucking limited to normal working hours of 12- 14 hours (between 7:00AM and 10:00PM). Noise Bylaw limits apply to afterhours activities. Estimate that tunnel spoils will be hauled away at 3 trucks per hour as the tunnel progresses approximately 20 m per day. Another 3 empty trucks will be arriving to the site each hour to be loaded. Tunneling will also require, on average, 3 trucks per day delivering parts for the tunnel lining. | Modest noise. Heavier trucking. |
| **June 2018** |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| East-West Tunnel (EWT) Tunneling | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2018 | Early February 2019 | 40-45 weeks (10 months) | TBM progressing along EWT. Spoils (crushed stones - gravel) being extracted from launch shaft and being trucked away. Tunneling 20-22 hours per day, but trucking limited to normal working hours of 12- 14 hours (between 7:00AM and 10:00PM). Noise Bylaw limits apply to afterhours activities. Estimate that tunnel spoils will be hauled away at 3 trucks per hour as the tunnel progresses approximately 20 m per day. Another 3 empty trucks will be arriving to the site each hour to be loaded. Tunneling will also require, on average, 3 trucks per day delivering parts for the tunnel lining. | Modest noise. Heavier trucking. |
| **July 2018** |
| Construction of Odour Control Building | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Mid May 2017 | Mid July 2018 | 50-55 weeks (13 months) | Typical building construction with material and equipment being delivered to site as required. | Modest noise. Modest trucking. |
| East-West Tunnel (EWT) Tunneling | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2018 | Early February 2019 | 40-45 weeks (10 months) | TBM progressing along EWT. Spoils (crushed stones - gravel) being extracted from launch shaft and being trucked away. Tunneling 20-22 hours per day, but trucking limited to normal working hours of 12- 14 hours (between 7:00AM and 10:00PM). Noise Bylaw limits apply to afterhours activities. Estimate that tunnel spoils will be hauled away at 3 trucks per hour as the tunnel progresses approximately 20 m per day. Another 3 empty trucks will be arriving to the site each hour to be loaded. Tunneling will also require, on average, 3 trucks per day delivering parts for the tunnel lining. | Modest noise. Heavier trucking. |
| **August 2018** |
| East-West Tunnel (EWT) Tunneling | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2018 | Early February 2019 | 40-45 weeks (10 months) | TBM progressing along EWT. Spoils (crushed stones - gravel) being extracted from launch shaft and being trucked away. Tunneling 20-22 hours per day, but trucking limited to normal working hours of 12- 14 hours (between 7:00AM and 10:00PM). Noise Bylaw limits apply to afterhours activities. Estimate that tunnel spoils will be hauled away at 3 trucks per hour as the tunnel progresses approximately 20 m per day. Another 3 empty trucks will be arriving to the site each hour to be loaded. Tunneling will also require, on average, 3 trucks per day delivering parts for the tunnel lining. | Modest noise. Heavier trucking. |
| **September 2018** |
| East-West Tunnel (EWT) Tunneling | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2018 | Early February 2019 | 40-45 weeks (10 months) | TBM progressing along EWT. Spoils (crushed stones - gravel) being extracted from launch shaft and being trucked away. Tunneling 20-22 hours per day, but trucking limited to normal working hours of 12- 14 hours (between 7:00AM and 10:00PM). Noise Bylaw limits apply to afterhours activities. Estimate that tunnel spoils will be hauled away at 3 trucks per hour as the tunnel progresses approximately 20 m per day. Another 3 empty trucks will be arriving to the site each hour to be loaded. Tunneling will also require, on average, 3 trucks per day delivering parts for the tunnel lining. | Modest noise. Heavier trucking. |
| **October 2018** |
| East-West Tunnel (EWT) Tunneling | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2018 | Early February 2019 | 40-45 weeks (10 months) | TBM progressing along EWT. Spoils (crushed stones - gravel) being extracted from launch shaft and being trucked away. Tunneling 20-22 hours per day, but trucking limited to normal working hours of 12- 14 hours (between 7:00AM and 10:00PM). Noise Bylaw limits apply to afterhours activities. Estimate that tunnel spoils will be hauled away at 3 trucks per hour as the tunnel progresses approximately 20 m per day. Another 3 empty trucks will be arriving to the site each hour to be loaded. Tunneling will also require, on average, 3 trucks per day delivering parts for the tunnel lining. | Modest noise. Heavier trucking. |
| **November 2018** |
| East-West Tunnel (EWT) Tunneling | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2018 | Early February 2019 | 40-45 weeks (10 months) | TBM progressing along EWT. Spoils (crushed stones - gravel) being extracted from launch shaft and being trucked away. Tunneling 20-22 hours per day, but trucking limited to normal working hours of 12- 14 hours (between 7:00AM and 10:00PM). Noise Bylaw limits apply to afterhours activities. Estimate that tunnel spoils will be hauled away at 3 trucks per hour as the tunnel progresses approximately 20 m per day. Another 3 empty trucks will be arriving to the site each hour to be loaded. Tunneling will also require, on average, 3 trucks per day delivering parts for the tunnel lining. | Modest noise. Heavier trucking. |
| **December 2018** |
| East-West Tunnel (EWT) Tunneling | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2018 | Early February 2019 | 40-45 weeks (10 months) | TBM progressing along EWT. Spoils (crushed stones - gravel) being extracted from launch shaft and being trucked away. Tunneling 20-22 hours per day, but trucking limited to normal working hours of 12- 14 hours (between 7:00AM and 10:00PM). Noise Bylaw limits apply to afterhours activities. Estimate that tunnel spoils will be hauled away at 3 trucks per hour as the tunnel progresses approximately 20 m per day. Another 3 empty trucks will be arriving to the site each hour to be loaded. Tunneling will also require, on average, 3 trucks per day delivering parts for the tunnel lining. | Modest noise. Heavier trucking. |
| **January 2019** |
| East-West Tunnel (EWT) Tunneling | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early April 2018 | Early February 2019 | 40-45 weeks (10 months) | TBM progressing along EWT. Spoils (crushed stones - gravel) being extracted from launch shaft and being trucked away. Tunneling 20-22 hours per day, but trucking limited to normal working hours of 12- 14 hours (between 7:00AM and 10:00PM). Noise Bylaw limits apply to afterhours activities. Estimate that tunnel spoils will be hauled away at 3 trucks per hour as the tunnel progresses approximately 20 m per day. Another 3 empty trucks will be arriving to the site each hour to be loaded. Tunneling will also require, on average, 3 trucks per day delivering parts for the tunnel lining. | Modest noise. Heavier trucking. |
| **February 2019** |
| Construction of Large Chambers (once tunneling complete) | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early February 2019 | Mid October 2019 | 35-40 weeks (9 months) | Construction of chambers includes the following components: micro piles installation, structure floor, walls and roof construction, ventilation duct, installation of gates, ladders and steps, and backfill. Materials and concrete being delivered to site as required. | Modest noise. Modest trucking. |
| Construction of Large Chambers (once tunneling complete) | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early February 2019 | Mid October 2019 | 35-40 weeks (9 months) | Construction of chambers includes the following components: micro piles installation, structure floor, walls and roof construction, ventilation duct, installation of gates, ladders and steps, and backfill. Materials and concrete being delivered to site as required. | Modest noise. Modest trucking. |
| **March 2018** |
| Construction of Large Chambers (once tunneling complete) | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early February 2019 | Mid October 2019 | 35-40 weeks (9 months) | Construction of chambers includes the following components: micro piles installation, structure floor, walls and roof construction, ventilation duct, installation of gates, ladders and steps, and backfill. Materials and concrete being delivered to site as required. | Modest noise. Modest trucking. |
| **April 2019** |
| Construction of Large Chambers (once tunneling complete) | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early February 2019 | Mid October 2019 | 35-40 weeks (9 months) | Construction of chambers includes the following components: micro piles installation, structure floor, walls and roof construction, ventilation duct, installation of gates, ladders and steps, and backfill. Materials and concrete being delivered to site as required. | Modest noise. Modest trucking. |
| **May 2019** |
| Construction of Large Chambers (once tunneling complete) | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early February 2019 | Mid October 2019 | 35-40 weeks (9 months) | Construction of chambers includes the following components: micro piles installation, structure floor, walls and roof construction, ventilation duct, installation of gates, ladders and steps, and backfill. Materials and concrete being delivered to site as required. | Modest noise. Modest trucking. |
| **June 2019** |
| Construction of Large Chambers (once tunneling complete) | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early February 2019 | Mid October 2019 | 35-40 weeks (9 months) | Construction of chambers includes the following components: micro piles installation, structure floor, walls and roof construction, ventilation duct, installation of gates, ladders and steps, and backfill. Materials and concrete being delivered to site as required. | Modest noise. Modest trucking. |
| **July 2019** |
| Construction of Large Chambers (once tunneling complete) | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early February 2019 | Mid October 2019 | 35-40 weeks (9 months) | Construction of chambers includes the following components: micro piles installation, structure floor, walls and roof construction, ventilation duct, installation of gates, ladders and steps, and backfill. Materials and concrete being delivered to site as required. | Modest noise. Modest trucking. |
| **August 2019** |
| Grading and Landscaping | Late August Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Late August 2019 | Early November 2019 | 16-20 weeks (4 months) | Will include hauling away granular material installed as a base for driving vehicles within the staging area and hauling in new topsoil for landscaping. This will be followed by bringing in and installing numerous trees throughout the park. It's estimated that hauling away the granular material would take approximately 2-3 weeks and result in approximately 2-3 trucks per hour during this two to three week period. It is likely that hauling in new topsoil could generate similar trucking at its peak, but would happen later in this period. | Modest noise. Heavier trucking. |
| Construction of Large Chambers (once tunneling complete) | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early February 2019 | Mid October 2019 | 35-40 weeks (9 months) | Construction of chambers includes the following components: micro piles installation, structure floor, walls and roof construction, ventilation duct, installation of gates, ladders and steps, and backfill. Materials and concrete being delivered to site as required. | Modest noise. Modest trucking. |
| **September 2019** |
| Grading and Landscaping | Late August Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Late August 2019 | Early November 2019 | 16-20 weeks (4 months) | Will include hauling away granular material installed as a base for driving vehicles within the staging area and hauling in new topsoil for landscaping. This will be followed by bringing in and installing numerous trees throughout the park. It's estimated that hauling away the granular material would take approximately 2-3 weeks and result in approximately 2-3 trucks per hour during this two to three week period. It is likely that hauling in new topsoil could generate similar trucking at its peak, but would happen later in this period. | Modest noise. Heavier trucking. |
| Construction of Large Chambers (once tunneling complete) | Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Early February 2019 | Mid October 2019 | 35-40 weeks (9 months) | Construction of chambers includes the following components: micro piles installation, structure floor, walls and roof construction, ventilation duct, installation of gates, ladders and steps, and backfill. Materials and concrete being delivered to site as required. | Modest noise. Modest trucking. |
| **October 2019** |
| Grading and Landscaping | Late August Site 5a (Stanley Park – Main Chamber and Odour Control Building Area) | Late August 2019 | Early November 2019 | 16-20 weeks (4 months) | Will include hauling away granular material installed as a base for driving vehicles within the staging area and hauling in new topsoil for landscaping. This will be followed by bringing in and installing numerous trees throughout the park. It's estimated that hauling away the granular material would take approximately 2-3 weeks and result in approximately 2-3 trucks per hour during this two to three week period. It is likely that hauling in new topsoil could generate similar trucking at its peak, but would happen later in this period. | Modest noise. Heavier trucking. |
|   |  |  |  |  |  |  |
| ***Important Notes:****1. The activities list is not intended to be an exhaustive list. Normal (a.k.a. daytime) working hours as defined in the city's Zoning Bylaw is 7:00AM-10:00PM. Outside of these hours (i.e. 10:00PM-7:00AM) is referred to as "afterhours”. The Contract Documents stipulate that the following activities will not be permitted afterhours: • Backing-up construction equipment and vehicles (due to backup alarm) • Handling sheet piling• Deliveries, including loading/unloading material or excavated muck into trucks • Tree removal, cutting or grinding• Operation of equipment, motors and power tools without noise dampening • Significant grading operations requiring earth-moving equipment The Contract Documents further stipulate that a noise monitoring program will be implemented by the Contractor to assess conformance to the stipulated limits. The noise monitoring program will be approved by the Contract Administrator prior to implementation. Exceedances will be reported to the Contract Administrator within 24 hours with a solution to prevent future exceedances. The City reserves the right to order the Contractor to cease the use of non-conforming equipment or to correct non-conforming procedures or to cease the nighttime construction activities at no cost to the City in the event that noise thresholds are exceeded.2. The column for noise trucking is intended to be a high-level relative comparison. A noisy activity is the label used for activities that include breaking rock, banging steel, etc; other activities are considered to generate modest noise (relative to breaking rock and banging steel). Similarly, heavy trucking is the label used for activities generating 3 to 4 trucks per hour on average; other activities are considered to generate modest trucking (considerably less than 3-4 trucks per hour).3. All work at Site 5c (River Lane / Queen Victoria) is limited to daytime activities. No work is currently permitted at this site afterhours (10:00pm to 7:00am). The Contractor may submit a special request for a specific task that is impractical to be completed during daytime, but it would need to be submitted for review and approval by the project team and the Councillor as it is not currently permitted.* |
|
|
|
|
|
|
|
|
|
|
|
|
|
|